## Slide 1: Title: Restoration of Livestock Services in conflict affected areas (RESTORE) Dr Wubet Sinshaw Amhara Region
Contracting authority: European Union
EU Individual Measure 3: Agricultural Recovery and Improved Domestic Food Production and Food Security in Ethiopia

## Slide 2: Outline
Project profile
Objectives
Working areas
Target Groups and Beneficiaries
Main Results – Outputs and activities
Project Organizational Structure
Coordination and management
Regional GVT Contributions in Kind

## Slide 3: Project profile
Title of the Program | EU IM 3: Support to Sustainable Livestock System in Ethiopia
Title of the action/the project | Restoration of Livestock Services in Conflict affected areas of Amhara Region
Name of the lead applicant | Amhara National Regional Bureau of Agriculture
Name of co-applicants | NA
Location of the action | Amhara National Regional State, Conflict affected areas
Duration of the action | 48 months

## Slide 4: Objectives
The overall Objective of the action :
Enhance food security, nutrition and livelihood resilience for rural communities in the region, with a special emphasis on areas affected by conflict with reduction of GHG emissions
The Specific objective of the action :
Sustainable recovery of the livestock system in conflict affected areas, improve overall sector productivity, marketing and limiting GHG emissions.

## Slide 5: RESTORE Project in Amhara Region
Working areas
14 focal and 20 non focal Woredas
Focal Woredas;
Menth-mama, Efratanagidim, Kemisie, Artuma Fursi, Desie, Kombolcha, Legambo, Rayakobo, Woldia, Gidan, Zikuala, Gunabegimidir, Laygayint, Adiarkay
Non Focal woredas
Simada, Ebnat, Belesa,Tach armachiho, Gonji-kolela, Goncha, Huleteju, Banja, Debark, Telemt, Mirab Armachiho, Ageremariam, Angolela, Jama,Woreilu, Mekdela, Bati, Wadila, Meket, Sekota

## Slide 6: Target Groups and Beneficiaries
Target Groups :
Regional veterinary laboratories
14 focal and 20 non focal (HEARD) Woredas
70 Private veterinary practitioners
200 Selected women and youth
Forage seed producer enterprises and cooperatives
Beneficiaries Include:
Livestock Producers
Livestock product processors
Livestock product consumers
Livestock Traders in the region
Women and youth groups
Indirect Beneficiaries
Amhara Regional Agricultural Research Institute
Universities (BDU, UoG, Debretabor, Wollo, woldiya)
Bordering regional states

## Slide 7
Main Results – Outputs
Result 4; Availability and Quality of livestock feeds improved through farmers/ pastoralists -private sector driven fodder production and marketing
Result 2; The quality and reliability of integrated public and private veterinary service delivery improved
Result 1; Livestock service delivery systems restored in conflict affected areas
Result 5: The quality of hide and skin enhanced through improved animal health intervention

## Slide 8: Main activities Result 1: Livestock services delivery systems restored in conflict affected areas
1.1. Conduct baseline assessment to determine current status of veterinary services in conflict affected areas
1.2. Equip 14 Veterinary clinics with basic veterinary equipment (ILRI)
1.3. Supply 14 Vet clinics with basic clinical consumables
1.4. Strengthen the diagnostic capacity of Kombolcha regional veterinary laboratory (ILRI)
1.5. Supply 14 motorbikes to selected conflict affected woredas

## Slide 9: Result 2: The quality and reliability of integrated public and private veterinary service delivery improve
2.1 Training need assessment for demand driven trainings
2.2 Strengthen existing Public and Private vet services delivery through trainings and technical follow up support
2.3 Strengthen the control and eradication of PPR disease by conducting PDS, outbreak investigation, Support regional PPR stakeholders (taskforce) meetings and Risk based vaccination
2.4 Support reduction of young and adult stock mortality in different production systems as herd health intervention through trainings & provision of materials including for poultry.
2.5 Strengthen the operational and technical capacity of the regional veterinary laboratory through purchase and supply of basic vet equipment’s, kits and consumables (Bahir Dar) (ILRI)
2. 6 Strengthen the capacity of regional veterinary laboratories through renovation and upgrading the standard of the facilities
2.7 Facilitate business start-up Credit support and provide awareness raising workshop for female & young veterinary graduates
2.8 Support the existing private animal health practitioners in non-focal woredas
2.9 Deliver Artificial insemination training for female & young veterinary graduates

## Slide 10: Result 4: Availability and Quality of livestock feeds improved through farmers/pastoralists -private sector driven forage and fodder production and marketing
  4.1 Support existing forage seed producers cooperatives and enterprises through trainings
  4.2 Support selected three existing forage seed producers cooperatives and three enterprises in feed packing, labelling, storage facility, marketing linkage,
  4.3 Support Feed processing unions/enterprises on feed formulation of quality feed
  4.4 Support farmers with improved livestock feed fodder production integrated within a mixed farming system or as a specialized crop for farmers through provision of improved forage seeds
  4.5 Support government and private nurseries to produce and distribute improved forage seeds through provision of capacity development trainings and basic materials (polythene tube, seed, etc)
  4.6 Study on the impact of brewery by-product on calf mortality and blindness (ILRI)

## Slide 11: Result 5: The quality of hide and skin enhanced through improved animal health intervention
5.1 Conduct assessment on existing skin and hide damaging diseases and develop strategies for the control of these diseases
5.2 Purchase and supply of ectoparasite control input (accaricide chemicals, Knapsack sprayers, personal protective materials and others)
5.3 Conduct stakeholders’ awareness creations on hide and skin quality
5.4 Provide Training on the control of skin and hide damaging diseases
5.5 Conduct control on the priority skin & hide diseases/Ectoparasite
5.6 Support the local extension service for the improvement of hide and skin production, processing and marketing

## Slide 12: G. Objective; Enhance food security, nutrition and livelihood resilience for rural communities S. Objective; Sustainable recovery of the livestock system in conflict affected areas
Outputs
Supply 14 Vet clinics with basic clinical Equipment and consumables
Supply 14 motorbikes
1.Delivery systems restored
2. The quality and reliability of integrated public and private vt service delivery improved
4. Availability and Quality of livestock feeds improved
5. The quality of hide and skin enhanced
Reinovate VET laboratories
Support the PPR eradication
Strengthen Strengthen the apacity of VET Lab (Bahir Dar) (ILRI)
Training for Public & Private vet Personnel
Support reduction of young and adult stock mortality
Training need assessment
Facilitate business start-up Credit support
Support the existing private AH practitioners in non-focal woredas
DeliverAI training
Conduct control on the priority skin & hidediseases/Ectoparasite
Provide Training on the control of skin damaging diseases
Conduct stakeholders’ awareness creations on skin quality
Supply and conduct ectoparasite control
Assessment on existing skin and hide damaging diseases
  Train Forage seed roducers
Support selected three existingforage seed producers cooperatives
  Support Feed pr
  Support Feed processing unions on feed formulation feeulation of quality feed
Support farmers with improved livestock feed fodder production
Support government and private nurseries
Support on the local extension service

## Slide 13: Project Organizational Structure
Regional Project steering Committee
BoA, Amhara Regional state
Regional Animal Health Directorate
Regional PC team
(Regional Project Coordination unit)
2 Regional Vet. Labs
14 focal and 20 non focal Woreda LRDP Offices
Federal PCU
MoA
Livestock production, Product and Forage Dvt Directorate
ALRDPO

## Slide 14: Coordination and management (both internal and external)
A/ Regional level: Under the Amhara regional Bureau of Agriculture (BoA).
Livestock Resource Development and Promotion Office
District Livestock offices
The woreda/district and zonal administrations
The project coordination unit will be responsible to lead the overall implementation of project activities.
B/ Federal Level: MoA, EU and Technical Assistant Team (TAT) will provide an overall coordination and technical support

## Slide 15: Organisational structure (Human resources)
Nr | Position title | number of employees | Months | Project site-Field based | Implementing Agency
1 | Project Manager | 1 |  |  | LRDPO
2 | Project Monitoring, Evaluation & Learning Expert | 1 |  |  | 
3 | Project Finance officer | 1 | 48 |  | 
4 | Project Accountant | 1??? |  |  | 
5 | Project procurement/casher and secretary | 1 |  |  | 
6 | Driver | 1 |  |  | 

## Slide 16: Other similar projects
The project works in collaboration with projects having similar objectives to minimize duplication of costs and efforts
Livestock and Fishery Sector Development Project (LFSDP).
FSRP/Food Systems Resilience Program for Eastern and Southern Africa
Others working on Livestock (Mapped)

## Slide 17: . Stakeholders (at Federal, Regional)
In order to enhance and improve the contribution of the sector, it will be vital to work with stakeholders to address the gaps and constraints identified in the sector.
At federal level:
The MoA and the TA team will be responsible for the overall coordination, technical support and monitoring of this projects including the follow up of the project financial utilization and Auditing,
At Regional level
Bureau of Labour and Training (BoLT)
Tsedey Bank
Women and children affair Bureau (BoWCA)
Universities
Private veterinary institutes and practitioners

## Slide 18: Monitoring and Evaluation
Project Monitoring and Evaluation mechanisms will be developed jointly by the project M&E expert and TA team to undertake structured and regular follow up of project performance, impact, reporting and documentation
Monitoring
Impact monitoring will involve an appropriate mix of quantitative and qualitative data collection and analysis.
Monitoring activities under this project will therefore invite members of the project steering group (Self monitoring) to jointly monitor project progress and provide feedback.
The European Commission and MoA may carry out joint field monitoring
Results Oriented Monitoring (ROM) will be deployed by the European commission via independent consultants,

## Slide 19: Evaluations:
The evaluation will be planned in collaboration with the, MoA, the TA team and the EU Delegation
An independent evaluations will be carried out by independent external evaluators:
The mid-term evaluation
The end of project evaluation

## Slide 20: Reporting
. Reporting: (Quarterly, Interim, annual and final implementation reports)

## Slide 21: Main means for the action
Nr | Type of Item | Total qty. | To be procured | Remarks
1 | Motorbikes | 14 | 14 | For selected districts to be Procured by ILRI
2 | Desk top Computers | 14 | 14 | For selected districts by Region
3 | Laptops + Hard Drives | 5 | 5 | For the Project staff
4 | All in-one printer | 1 | 1 | For Project office
5 | UPS | 5 | 5 | For project staff
6 | Tables | 3 | 3 | For Project staff
7 | Swivel chair | 3 | 3 | For Project staff
8 | File cabinet | 2 | 2 | For Project staff
9 | Tablet | 1 | 1 | For project office
10 | 4G WIFI Modem | 2 | 2 | For project office and Regional team
11 | Furniture (Drug storage, shelf, File cabinet, Lab Table) | Set | Set | For 10 Vet. Clinics in target Woredas
12 | Safe box | 1 | 1 | For project Office

## Slide 22: Regional GVT Contributions in Kind
Government contribution in kind is important to ensure ownership and commitment for sustainability of the works. Thus, the lead applicant, BoA/ALDPO will be responsible to provide contribution in kind.
1. Contribution of vehicles
2. Contribution of government technical staffs
3. Working office for PMU
NB: The total estimated cost of in-kind contribution is EUR 354,048.

## Slide 23: Visibility
Communication and visibility of the EU is a legal obligation for all external actions funded by the EU.
The measures shall be implemented by demonstrating the EU support in publications, newsletters , sticker of EU logo/stickers stamped on---, photograph and videos will also be recorded, Banners and posters, brochures, handbooks and leaflets
Make understanding by the beneficiaries and other stakeholders that the Action is funded by the EU. During
meetings, awareness raising events, trainings and workshops, etc,
EU be Acknowledged verbally and in writing.

## Slide 24: Mainstreaming/Cross cutting issues
  1. Environmental Protection & Climate Change (reduction of GHG)
2. Gender equality and empowerment of women and girls
3. Disability
4. Reduction of inequalities
5. Democracy
participation, accountability, non-discrimination, transparency and legality.
6. Conflict sensitivity, peace and resilience
The proposed action will apply a do no harm and conflict sensitivity approach.

## Slide 25: Planning
Planning.docx

## Slide 26: Budget summary
Activities | Years | Year 12 | 
Activities | Total Cost (in EUR)3 |  | Total Cost (in EUR)
1. Human Resources | 341,500.00 |  | 122,020.00
2. Travel6 | 30,800.00 |  | 20,800.00
3. Equipment and supplies7 | 305,898.00 |  | 240,398.00
4. Project office14 | 93,600.00 |  | 23,400.00
5. Other costs, services8 | 56,200.00 |  | 10,832.00
6. Other | 655,000.00 |  | 133,250.00
7. Subtotal direct eligible costs of the Action (1-6) | 1,482,998.00 |  | 550,700.00
8. Indirect costs (maximum 7% of 7, subtotal of direct eligible costs of the Action) | 103,809.86 |  | 38,549.00
9. Total eligible costs of the Action, excluding reserve and volunteers' work (7+ 8) | 1,586,807.86 |  | 589,249.00
10. Provision for contingency reserve (maximum 5% of 7 'Subtotal of direct eligible costs of the Action') | 74,149.14 |  | -
Extra purchase | 317,000 |  | 
11. Total eligible costs (9+10) | 1,977,957 |  | 589,249.00

## Slide 27
THANK YOU
EUROPIAN UNION