## Slide 1
Innovation platforms in the imGoats project: Lessons learned
Kees Swaans
Small ruminant value chains for reducing poverty and increasing food security in dryland areas of India and Mozambique
ILRI Internal meeting on
Innovation Platforms, Nairobi
6-7 December 2012

## Slide 2: Content
Introduction
IPs in the context of imGoats
What went well (successes)?
What went less well (failures)?
How was the IP organized?
Issues of implementation
Lessons learned
2

## Slide 3: Introduction
imGoats is about reducing poverty and increasing food security in dry areas of India and Mozambique through improving goat value chains
Objectives
  Piloting organizational and technical models for goat value chain development
  Documenting, communicating and promoting appropriate evidence-based model(s) for sustainable, pro-poor goat value chains
3

## Slide 4: Target group & area
In India:
Scheduled Tribes, Scheduled Castes and Other Backward Castes
Udaipur district in Rajasthan State  2,600hh
Dumka district in Jharkhand State  2,000hh
In Mozambique:
at least 25% Female Headed Households and families living with HIV/AIDS
Inhassoro district in Inhambane province  500hh
4

## Slide 5: Target area
5
Source: http://geology.com/world/world-map.shtml
Udaipur
Dumka
Inhassoro

## Slide 6: The approach
Resulting from willingness to do research differently, project implementation is done through two NGO’s:
  BAIF in India and
  CARE in Mozambique.
ILRI has 2 post-doc researchers based at the NGO’s offices, ensuring a close day-to-day collaboration and action research
The project applies an Innovation System approach in the context of value chains
Outcome Mapping is used as monitoring and evaluation tool.
6

## Slide 7: Impact pathway IPs
7
Innovation Platforms
(Producer) Hubs
Improved communication and co-ordination among VC actors
Improved access of producers to services and markets
Improved productivity through technical & service delivery interventions
Changes in Knowledge, Attitudes, Capacity and Practices of producers and other VC actors
Improved Incomes
Reduced poverty
Enhanced food security and nutrition
Improved benefits from VC for various actors

## Slide 8: What went well?
Technical and institutional constraints have been identified through engagement with stakeholders, baselines, and joint diagnosis
Similar challenges in both countries
  Production (breeding, animal health, and feed)
  Lack of coordination among producers and between VC actors
8

## Slide 9: What went well?
IPs established and meet regularly (2-3 monthly) for problem identification, action planning and monitoring
IP are functioning and facilitated by resp. field guides (Udaipur) and a secretariat (Inhassoro)
9
Picture from India?

## Slide 10: What went well?
Producers (from Goat PGs) well represented
Diagnosed technical and capacity needs and opportunities and final jointly developed strategy for addressing them
Feedback on research results and actions
10

## Slide 11: What went less well?
Takes long time for IP member to understand what IP is about; may still not be completely clear
Consistent participation of goat keepers problem
Involvement of other VC actors so far limited (esp. buyers; season dimension)
Challenge to involve women in IP
11

## Slide 12: What went less well?
Information exchange between Goat PGs and IPs
Continuity/sustainability of IPs (esp. in Inhassoro)
Weak IP facilitation skill among local actors
Goat keeping secondary activity (low input-cost system); commercial goat keeping requires change in mind-set among producers and supportive institutions and a long term process
12
Picture from India?

## Slide 13: Organization
NGOs (BAIF and CARE) acted initially as ‘knowledge broker’ and facilitators; later taken over by ‘field guides’ in India and elected IP secretariat (VC actors) in Mozambique (still needs strong support from NGOs)
Agenda setting: Mozambique - CARE/ILRI took the lead in agenda-setting in the first 5 meetings (with accordance from IP secretariat); India – initially BAIF/ILRI setting agenda; now standardized format depending on action plans
Held 2-3 monthly; first few meetings focused on identification of constraints and development of action plans; later report back on activities and follow up
13

## Slide 14: Implementation
Timely implementation of activities sometimes problematic due to availability of vaccines / vet. drugs, local festivals, etc. (India)
14

## Slide 15: Implementation
Transport costs/long distances (Mozambique)
Translations; preparations/reports in English, IP meetings in Xitswa translated in Portuguese (resource intensive) (Mozambique)
In general resource intensive (human and/or financial)
Facilitation skills local actors weak
15

## Slide 16: Lessons learned
Coordination among goat producers and other value chain actors was limited. In this context, an IP provides a mechanism for communication and information exchange in order to enhance collective action
Broad scoping/diagnosis, VCA, and Gender Analysis, should be conducted during inception phase of project
16

## Slide 17: Lessons learned
Focus in both countries is evolving over time, starting with production issues and graduating towards commercialization
Relevant issues and hence participation of actors season dependent in case of goat meat VC.
17

## Slide 18: Lessons learned
Information exchange within and especially beyond the platform is crucial to ensure that the IP is based on relevant issues and are taken forward
IPs tend to be time and (human) resource intensive processes; continuity/sustainability depends on capacity to resolve VC constraints; needs to be clear to different VC actors what they will get out of participation
IP processes should be used in goat VC projects of at least 3 years. However, they should not be seen as permanent structures. IPs could be used as starting point for other forms of collective action (e.g. hubs).
18

## Slide 19: Questions
Representation issues; who is included/excluded; and what are the power dynamics? (need for monitoring)
Research/documentation is intensive; to what extent should this be done by researchers and/or by local actors themselves, and to what extent part of process
R4D; to what extent are research and development integrated, and how is that reflected in the IP
What can we learn from R4D Partnerships
19

## Slide 20
International Livestock Research Institute (ILRI)
Better lives through livestock
Animal agriculture to reduce poverty, hunger and environmental degradation in developing countries
www.ilri.org
Thank You!