## Slide 1: HEARD Project Final Evaluation
HEARD Overall Project Brief
Melaku Assefa
MoA HEARD coordinator
25 March 2024
International Livestock Research Institute (ILRI) Ethiopia

## Slide 2: Presentation outline
Introduction
Main activities
Response to the impact of COVID-19 on Animal Health
Project management
Project M&E
Challenges
Lessons
Overall performance

## Slide 3: Introduction
HEARD (Health of Ethiopian Animal for Rural Development)
Project, C. No: ET/FED/040-392
Financed from the 11th EDF
Total budget is EUR 15, 000, 000
Duration of the implementation phase initially was 48 months. (Dec 2018 -Dec 2022)
No-cost extension was allowed for one additional year,

## Slide 4: Introduction...
No | Project Component | Implementing Agency | Contracting Authority | Modality | Budget in EUR | Remark
1 | Component 1 | Regional Bureaus (Am, Oro & Som) | MoF /NAO | Indirect Grant cont | 6 Mil. | 0.75 mil for other costs
2 | Component 2 | ILRI & EVA | MoF /NAO | Indirect Grant cont | 3.8 Mil. | 
3 | Component 3 | MoA | EC | Direct Grant cont | 1.9 Mil. | 
4 | Supply Procurement to MoA & Regions | MoA/EUD | MoF /NAO | Supply cont | 1.1 Mil. | 
5 | Service procurement/ TA to MoA & regions | MoA | MoF /NAO | Service cont | 1.45 Mil. | 
Total | Total |  |  |  | 15 Mil | 

## Slide 5: Main activities
The Overall objective /Goal/Impact:
Increase sustainable livestock productivity and improve the marketing of livestock products.
The Specific Objective /purpose/ Outcome:
Quality and reliability of integrated public and private veterinary service delivery improved taking into account the increasing impacts of climate change.

## Slide 6: Main activities...
Results/ intermediate out comes/Components:
1. Strengthening the quality of public and private veterinary services and delivery through the creation of an enabled and rationalized environment.
2. Improving the technical competences (knowledge, skills and attitude) and incentives for veterinary service providers to deliver better and rationalized services.
3. Improving the food safety of primary products of animal origin and better control of Zoonotic diseases achieved.

## Slide 7: Main activities...
Major Activities under result / Component 1: Strengthening the quality of public and private veterinary services:
1.1 Raise the quality of Veterinary Service performance by adopting OIE Performance of Veterinarian Services (PVS) and Gap analysis recommendations;
1.2 Enhance laboratory human and material diagnostic capacity;
1.3 Improved disease surveillance, disease control, and risk-based vaccination programs;

## Slide 8: Main activities...
1.4 Pilot innovative and gender sensitive animal health approaches;
1.5 Create an enabling environment for rationalization:
1. 6 Improve the quality of sheep and goat skin production;

## Slide 9: Main activities...
Major Activities under Result / Component 2: Technical competencies (knowledge, skills, and attitude) and incentives for veterinary service providers improved;
2.1 Pilot the Veterinary Privatization Road Map;
2.2 Develop training materials and implement innovative delivery methods;
2.3 Make available and disseminate resources for animal health knowledge.

## Slide 10: Main activities...
Major activities under the result / Component three: “Food safety of primary products of animal origin improved and better control of zoonotic diseases achieved” :
3.1 Improve inspection and certification of animal and animal products to ensure food safety;
3.2. Standardize and certify export abattoirs;
3.3. Support animal quarantine to strengthen inspection and certification;

## Slide 11: Main activities...
3.4. Strengthen the Livestock identification and traceability system (LITS);
3.5. Promote and implement standardized animal welfare;
3.6. Improve testing of primary animal products;
3.7. Develop University/College based meat inspection course to produce certified meat inspectors:
3.8. Enhance Zoonotic disease surveillance and control:

## Slide 12: Project management
Each project has PCU,
Each PCU is led by the animal health lead of the institution;
The project overall is led by the Steering committee, composed of higher officials of MoA /SMLFRD, Regions LR/PD Beauros’, ELRI/EVA, NAO and EUD;
MoA/SMLFRDS Oversees the project’s overall implementation;

## Slide 13: Project M&E
Internal:
Monitored by each project owner institution;
There is a joint monitoring platform of Major stakeholders facilitated by TAT;
External:
ROM mission recruited by EU
Mid-term evaluation recruited by HEARD
The current final evaluation;

## Slide 14: Response to the Impact of COVID-19 on Animal Health
Grant Contract ref: HEARD FED/2020/419-557
Budget EUR 400,000,
Results/outputs:
Veterinary drug supply and vaccination coverage improved;
Animal Health workers and value chain actors protected from COVID-19 infection;
Change of attitude on pro-COVID-19 precautions as a result of awareness creation;

## Slide 15: Challenges
COVID-19 Pandemic: Movement and gathering restrictions,
Security (instability): Movement restrictions,
Drought occurrence in different regions
Lengthy procurement procedure and lack of local suppliers for technical items;
Microfinances collateral and high interest rate;
Utilizing 10% reimbursable budget,

## Slide 16: Lessons
The importance of working in collaboration with partners, stakeholders, and beneficiaries ;
The importance of working from home and virtual meetings when necessary;
The necessity and benefits of establishing the revolving fund and cost-sharing mechanisms ;
Strong linkage between the public and private sectors for successful accomplishment;
The importance of frequent monitoring and technical support;

## Slide 17: Overall performance
Budget utilization +- 90%
The performance of technical activities is also expected to be the same.

## Slide 18
The end,
Thank you for listening!